## Data
Legend - Colour coding for each task's status on the graph, based on codes (1-4) selected in Status column.
[7 empty] | 1 | 2 | 3 | 4
Task/Milestone Name Error Message | Task/Milestone | Status (select 1-4 for each line) | Start Date dd-mm-yyyy | Scheduled Completion Date dd-mm-yyyy | Revised Completion Date dd-mm-yyyy | Duration (days) | = Not Yet Started | = Task Completed | = No Concern | = Concern | Overdue (days) | Length | 30
| Type task name here. | 1 | 2021-04-01 | 2021-05-25 | 2021-05-30 | 54 | 54 |  |  |  | 5 | 21 | 30
| Task 2 | 2 | 2021-04-30 | 2021-06-14 | 2021-06-19 | 45 |  | 45 |  |  | 5 | 6 | 30
| Task 3 | 4 | 2021-05-01 | 2021-07-04 | 2021-07-09 | 64 |  |  |  | 64 | 5 | 6 | 30
| Task 4 | 4 | 2021-05-15 | 2021-07-24 | 2021-07-29 | 70 |  |  |  | 70 | 5 | 6 | 30
| Task 5 | 1 | 2021-05-31 | 2021-07-20 | 2021-07-25 | 50 | 50 |  |  |  | 5 | 6 | 30
| Task 6 | 1 | 2021-06-01 | 2021-07-16 | 2021-07-21 | 45 | 45 |  |  |  | 5 | 6 | 30
| Task 7 | 1 | 2021-06-15 | 2021-07-30 | 2021-08-04 | 45 | 45 |  |  |  | 5 | 6 | 30
| Task 8 | 3 | 2021-06-30 | 2021-08-14 | 2021-08-19 | 45 |  |  | 45 |  | 5 | 6 | 30
| Task 9 | 1 | 2021-07-01 | 2021-07-01 | 2021-07-16 | 0 | 0 |  |  |  | 15 | 6 | 30
| Task 10 | 1 | 2021-07-15 | 2021-07-15 | 2021-07-20 | 0 | 0 |  |  |  | 5 | 7 | 30
| Task 11 | 2 | 2021-07-31 | 2021-09-14 | 2021-09-19 | 45 |  | 45 |  |  | 5 | 7 | 30
| Task 12 | 4 | 2021-08-01 | 2021-09-15 | 2021-08-01 | 0 |  |  |  | 0 | -45 | 7 | 30
| Task 13 | 1 | 2021-08-15 | 2021-09-15 | 2021-08-01 | -14 | -14 |  |  |  | -45 | 7 | 30
| Task 14 | 4 | 2021-08-15 | 2021-09-29 | 2021-10-04 | 45 |  |  |  | 45 | 5 | 7 | 30
| Task 15 | 1 | 2021-09-01 | 2021-10-16 | 2021-10-21 | 45 | 45 |  |  |  | 5 | 7 | 30
| Task 16 | 4 | 2021-09-01 | 2021-10-16 | 2021-10-21 | 45 |  |  |  | 45 | 5 | 7 | 30
| Task 17 | 3 | 2021-10-01 | 2021-11-15 | 2021-11-20 | 45 |  |  | 45 |  | 5 | 7 | 30
| Task 18 | 3 | 2021-11-01 | 2021-12-16 | 2021-12-21 | 45 |  |  | 45 |  | 5 | 7 | 30
| Task 19 | 4 | 2021-11-01 | 2021-12-16 | 2021-12-21 | 45 |  |  |  | 45 | 5 | 7 | 30
| Task 20 | 4 | 2022-01-01 | 2022-02-09 | 2022-03-25 | 39 |  |  |  | 39 | 44 | 7 | 30
Note on A3: If your Task/Milestone name is too long, this column will display a warning message.
Note on B3: 30 characters maximum.

## Instructions
Instructions:
Do a “Save As” to your local drive.
Populating your Gantt Chart (in the "Data" tab below):
NOTE: When typing numbers into the cells, type only the number (i.e. 20). Do not enter symbols (i.e. %) as they will change the format of the numbers in the cells/chart.
1. Only type in the cells on the Data sheet that are in blue font. The other cells have formulas which will automatically populate when you add information to the blue cells.
2. Type a short descriptive name for each task or milestone in the Task/Milestone column. To delete unneeded rows: If there are too many task lines in the template, right click on the task line (so the entire line is highlighted) and choose delete.
NOTE: The Task/Milestone Error Message column displays a warning message if your Task/Milestone name is too long. The maximum number of characters in the Task/Milestone name is 30.
3. Insert your dates in the format: dd/mm/yyyy, note that this will be shortened to only day-month in the Gantt Chart.
4. Note that there is a column for Scheduled Completion Date and Revised Completion Date. The Revised Completion Date column should be used:
a) to reflect a change in planned completion date e.g., to an earlier or later date than expected; and
b) to reflect the actual completion date of the task, whether it completes early or late. If the task completes on time, this column may be left blank. If the task runs shorter, the bar on the graph will shorten, if it runs longer the bar will extend, and change colour to show how far beyond the originally Scheduled Completion Date, the task has gone.
5. Use the Status column to set the colour of the bars that appear on the graph. Note the legend above the data table and insert the number correlating to the status of each task (i.e. If the task has not yet started, put a 1, and the bar will turn blue to indicate this).
6. Update Status and Revised Completion Dates each quarter
Preparing the Gantt Chart Display (in the "Chart" tab below):
1. Click on "Type Chart Title Here" to rename your chart.
2. Click in the text box at the lower left-hand corner to enter information about the chart (date prepared, source of data, report contact, etc.)
3. If applicable, enter Annotations into the chart by clicking on the Annotations icon. This box should be moved to point to the appropriate data point on the Chart. If more than one Annotation is needed, copy and paste the box. If no annotations are necessary, delete the box.
4. If applicable, use the Milestone icon and text box to identify important project milestones worthy of highlighing on the chart. Copy and paste the milestone to the correct location on the graph (in line with a task bar at the date the Milestone is planned to be complete), and type text into the text box to briefly describe the Milestone.
5. Based on your data and current knowledge, choose the appropriate red or green "stoplight" button for the current quarter from the right and copy/paste into the blank circle in the upper left corner of the chart. If historial data are available, copy/paste the red or green "stoplight" for each quarter into the blank circles in the upper right corner of the chart. The following definitions can be used as guidelines:
GREEN = Measure is on target and expected to maintain progress. No action is required.
RED = Measure is off target. Measure is expected to remain off target in the next report period unless Corrective Action is initiated. Project requires immediate follow-up.
Annotations
MILESTONE: